## IIB
EDIS Full Load Deployment Plan
Java Prod servers: |  | pgv0145a6 : 172.26.3.190
QA Servers (for reference and Bindings) |  | EDIS QA server : qgv012efb
RIT for firewall |  | NA
Interface Covered - |  | GroceryOrder
EG Groups - |  | es00ed00-07, and with 1 GB JVM heap size
S.No. | Step | Task | Description | Owner | Dependency | Duration | Start Date | End Date | Status | Remarks
1 | Prepare for Cutover |  |  | Colin | Production CR
Finalize cutover plan and checklists
Communicate cutover plan to deployment teams
Communicate go-live timeline to down streams
2 | Kafka Inbound Topic creation | Create Kafka Topic in Production server | OSMS-EMOM_C02_ORDER | Robert
3 | Kafka Inbound Topic Verification | Verify Kafka Topic in Production server | Verify if the topic OSMS-EMOM_C02_ORDER is created in Prod. | Robert
4 | Kafka Outbound Topic creation | Create Kafka Topic in Production server | ESED_C01_GroceryOrder | Robert |  | 15 mins
5 | Kafka Outbound Topic Verification | Verify Kafka Topic in Production server | Verify if the topic ESED_C01_GroceryOrder is created in Prod. | Robert |  | 15 mins
6 | Create JNDI bindings | Create JNDI bindings | NA | Robert |  | 15 mins
7 | Place and verify Property file in linux server | Place the extract and trigger property files | Extract properties file | Robert |  | 5 mins
8 | Create ESP job scheduler | ESP job scheduler in Prod | NA | Alex
9 | Setup OGG | Set up OGG | NA | Gordon
10 | Deploy IIB Application | Deploy & enable IIB application flows deployment folders: IIB /appl/spool/deploy/ESEDA IIB /appl/spool/deploy/ESEDB PS: The publisher flow used reading from Kafka Inbound Topic , then using the IIB for validations and transformation logic and then pushing the data to Kafka Outbound Topic. | ESED_GroceryOrder_eRUMS_IH_Publisher | Karen |  | 15 mins
11 | Start ESP job scheduler | Start ESP job scheduler in Prod | NA | Alex
12 |  | Smoke test and verification | NA | EDIS full load team / ESED Support teams | Steps 2 to 8 to be completed | 15 mins
|  |  | NA | EDIS full load team / ESED Support teams
13 | Verify Production Readiness - Comms | Communicate the deployment completion |  | Colin
14 | Inform EDM for Retail Store Full Load. | Remind EDM to check any impact before doing full load for Retail Store for OMS. | Remind EDM to check any impact before doing full load for RetailSection for OMS. | EDIS full load team / ESED Support teams
15 | Unsubscribe - EDM from Kafka topic - ESED_C01_GroceryOrder_FL | This full load is for OMS. Unsubscribe EDM from kafka topic ESED_GroceryOrder_FL before triggering full load for OMS. | This full load is for OMS. Unsubscribe EDM from kafka topic ESED_C01_GroceryOrder before triggering full load for OMS. | Robert
16 | Subscribe - EDM to Kafka Topic - ESED_C01_GroceryOrder_FL | Subscribe EDM again to the topic ESED_GroceryOrder_FL once full load for OMS is complated for GroceryOrder | Subscribe EDM again to the topic ESED_C01_GroceryOrder once full load for OMS is completed for GroceryOrder | Robert